## Project Phases
Task Division and Responsibilties
Phase-1
Team Members | Responsibilty | Task Given Date | Task Completed Date | Task Type | How I have done? Or Approach on doing it | Status
Sahithi, Vikranth | Data Cleaning | 2023-02-15 | 2023-02-27 | Handling missing values | Deleting missing values, Imputing missing values, Marking missing values | TRUE
|  |  |  | Removing duplicates |  | TRUE
|  |  |  | Handling outliers |  | TRUE
|  |  |  | Resolving inconsistencies |  | TRUE
|  |  |  | Handling data formatting issues |  | TRUE
Rahul | Building a model | 2023-02-28 |  | Gather and preprocess data | cleaning, transforming, and filtering the data. | TRUE
|  |  |  | Finding a Recommendation algorithm | Types of algorithms required to study and research on including collaborative filtering, content-based filtering, and hybrid approaches | TRUE
|  |  |  | Training and evaluating the model | This involves splitting the data into training and testing sets, training the model on the training set, and evaluating its performance on the testing set. You may need to iterate on this process multiple times to improve the model's accuracy and relevance. | TRUE
Prathyusha, Anusha | API Generation | 2023-02-19 |  | Google Places API | Local Search, Location-Based Service | TRUE
|  |  |  | Yelp API |  | TRUE
Phase-2
Team Members | Responsibilty | Task Given Date | Task Completed Date | Task Type | How I have done? Or Approach on doing it | Status
Sahithi, Vikranth | Data Visualisation | 2023-03-01 | 2023-03-07 | Understanding User Data | Helping developers to understand user behavior, identify user needs, optimize chatbot performance, and present data to stakeholders in a more compelling way. | TRUE
|  |  |  | Identifying User Needs |  | TRUE
|  |  |  | Testing and Evaluation |  | TRUE
|  |  |  | Presenting Data to Stakeholders |  | TRUE
Anusha | Building a model | 2023-03-01 |  | Generating Model | Prediction, Understanding model, Decision Making, Optimization, Testing | TRUE
|  |  |  | Finding the accuracy | Evaluation, Comparison, Confidence | TRUE
|  |  |  | Documenting user manual |  | TRUE
Prathyusha, Rahul | 1st stage of UI | 2023-03-01 |  | HTML, CSS, and JavaScript | They can be used to create a responsive and visually appealing UI for a chatbot. | TRUE
|  |  |  | UI frameworks and libraries | React, Angular, and Bootstrap, used to speed up development and ensure a consistent and professional look and feel. | TRUE
|  |  |  | Chatbot platforms | There are several chatbot platforms that provide tools and APIs for building chatbots, such as Dialogflow, IBM Watson, and Amazon Lex. | TRUE

## Prathyusha
Individual Work Flow
Task | Start Date | Type | Status | Queries
Problem Statement Suggestion |  | Cost price analysis of Automated cars | Completed | Proposed various fields we can use for developing the predictable techonolgy in Automative sector and faced some drawbacks
Dataset Identification |  | Canadian Tourist attractions | Completed | Helped in searching for datasets relatable for this dataset
API Generation | 2023-02-19 | Google API | Completed | Used Google places API for getting the location of the place
Use case generations | 2023-03-03 | How the UI Looks Like | In-Progress
Web Page mode of design |  | Components of UI | In-Progress
Requirements for design |  | RAW MetaData code | In-Progress

## Sahithi
Individual Work Flow
Task | Date | Type | Status | Queries
Problem Formulation | 2023-01-27 | suggested various ideas regarding the changes and factors in marketing industry | Completed | There are always going to be new marketing challenges and opportunities as technology and consumer behavior change. Current marketing issues include, among others. Data security and privacy, Automation, and artificial intelligence, Striking a balance between innovation and economics; the growth of social and digital media; the impact of marketing measurement.
Research | 2023-02-03 | Our team had several difficulties identifying the elements needed to build chatbots when conducting the research for the recommendation system. I have therefore recommended a few entities that might be beneficial for creating the dataset | Completed | Recommanded entities like the state, state names, city and phone number, ratings and number of reviews.
Contribution in Data Collection | 2023-02-10 | Canada camp cities Canada cities Canada statistics | Completed | I began looking for datasets at that time. I discovered a few datasets that might be helpful in developing the recommendation system
Suggestions in Building Business model | 2023-02-17 | Restuarants.xls | Completed | Creating a business model is crucial for any project. I then made some suggestions on how to fund our initiative. Some of them include approaching local businesses and using reviews from social media resources like google reviews and trip advisor reviews and trivago reviews
Data Cleaning | 2023-02-23 | Restuarants.xls | Completed | Data cleaning is a vital stage in data analysis that involves finding data anomalies and fixing or deleting flaws, inconsistencies, and inaccuracies in the dataset. The data is cleaned using Microsoft Excel.
Data Visualization | 2023-03-06 | Restuarants.twbx | completed | We have basically visualized “restaurants.xls” data using tableau to explain and visualize our data to the financial sponsors and stakeholders who aren’t having technical knowledge about data and also to the owners of local businesses with whom we are intending to get partnership. In this current visualizations, I’ve generated “Cuisine Wise Ratings & Reviews” and “Province Wise Top 5 Cuisine Types” charts. The dashboard has been generated by integrating the charts done by both me and my teammate Vikranth

## Anusha
Individual Work Flow
Task | Date | Type | Status | Queries
Problem Statement Formulation |  | Health Care domain and Retail Industry | Completed | Suggested project in healthcare and retail industry
Dataset identification |  | Canadian Recommendation System | Completed | While discussing the parameters and prior knowledge required in healthcare and retail industry, rejected that and confirmed Recommendation System
API Generation | 2023-02-19 | Yelp API | Completed
Model Selection | 2023-03-04 | Resturants.csv | In process | Selected Random forest Regressor Model for model fittng. But while implementing faced so many issues in converting the Categorical to Numerical. Implemented a model for one Cuisine Type i.e Steak House. But unable to figure out to implement it for every other type of Cuisine Type.
Model Parameters Identification | 2023-03-05 | Key Parameters for features and target | In process
Model testing | 2023-03-06 | Choosing the algorithm | In process

## Rahul
Individual Work Flow
Task | Date | Type | Status | Queries
Problem Formulation and finding the business case | 2023-01-27 | Project Ideas Related to Customer Segmentation and Social Media Analytics | Completed
Data Collection | 2023-02-10 | Filtered various datasets and Finalising | Completed
Model building | 2023-02-17 | Restuarants.xls, Things to watch | In-progress
Desiging the UI | 2023-02-23 | Part of UI component design | In-progress

## Vikranth
Individual Work Flow
Task | Date | Type | Status | Queries
Problem Formulation | 2023-01-27 | Project Ideas Related to Customer Segmentation and Social Media Analytics | Completed | Proposed various ideas for developing Mobile App using Customer Segmentation and Social Media Analytics
Research | 2023-02-03 | Rejection for previous Ideas | Completed | But Rejected the previous one because of the drawbacks
Contribution in Data Collection | 2023-02-10 | Canadian Tourist Attractions | Completed | Multiple discussions later, finalized the recommendation system
Data Exploration and Relationship between entities | 2023-02-17 | Restuarants.xls | Completed | Worked on the relationship between entities and how can be integrated to the chatbot
Data Cleaning | 2023-02-23 | Restuarants.xls | Completed | At first, faced some issues in cleaning but removed the duplicates and null values
Data Visualization | 2023-03-06 | Restuarants.twbx | Completed | City wise top 5 Cuisine types, Most famous Cuisine for Province and Dashboard.